## Sheet1
Tender Notice Process s Work plan
Sl.No | Screens and Functionality | Start date | End date | Status
1 | Designing of the Tender Notice | 2021-09-06 | 2021-09-08 | In-progress
2 | Designing of the Appendum Tender Notice | 2021-09-08 | 2021-09-13 | To-do
3 | List of requisition for E-bidding and database design for Tender notice | 2021-09-13 | 2021-09-13 | To-do
4 | Prepare tender notice and Its Edit With Submitting for Approval with Proper validation | 2021-09-13 | 2021-09-14 | To-do
5 | Approval process of tender notice and Publish | 2021-09-15 | 2021-09-15 | To-do
6 | List of approved /Published/Rejected tender notice | 2021-09-16 | 2021-09-16 | To-do
7 | Weekly testing in the server the tender Prepartion process | 2021-09-17 | 2021-09-17 | To-do
8 | List of Experied tender for E-bidding and database design for Addendum Tender notice | 2021-09-20 | 2021-09-20 | To-do
9 | Prepare tender notice and Its Edit With Submitting for Approval with Proper validation | 2021-09-20 | 2021-09-21 | To-do
10 | Approval process of tender notice and Publish | 2021-09-22 | 2021-09-22 | To-do
11 | List of approved /Published/Rejected tender notice | 2021-09-22 | 2021-09-22 | To-do
12 | Bid Notice Generation and Retrving the from database as Report | 2021-09-22 | 2021-09-24 | To-do
13 | Testing the Hosting the Adddendum tender notice process | 2021-09-24 | 2021-09-24 | To-do
14 | UOM Intergration | Depending on KD mam |  | To-do
15 | Dashboard development | 2021-09-27 | 2021-09-27 | To-do
16 | Reports |  |  | To Do
17 | EDMS Intergration |  |  | To-do

## Sheet3
Notice | open tender | Dosemetic | Works | template 1
Notice | open tender | international | Goods | template 1
Notice | open tender | Dosemetic | sevices | template 1
Tender | open tender | Dosemetic | consultancy | template 2
Tender | open tender | international | non consultancy | template 3
Tender | Restricted Tender | international | Works | template 2
Contarct | Restricted Tender | Dosemetic | Goods | template 3
Contarct | Restricted Tender | Dosemetic | sevices | template 1
Contarct | Restricted Tender | international | consultancy | template 1
Notice | Restricted Tender | international | non consultancy | template 1
Notice | Single Stage | international | Works | template 2
Notice | Single Stage | international | Goods | template 2
Tender | Single Stage | Dosemetic | sevices | template 2
Tender | Single Stage | Dosemetic | consultancy | template 2
Tender | Single Stage | Dosemetic | non consultancy | template 2
Contarct | Two-Stage | Dosemetic | Works | template 2
Contarct | Two-Stage | international | Goods | template 3
Contarct | Two-Stage | Dosemetic | sevices | template 2
Contarct | Two-Stage | international | consultancy | template 3
Contarct | Two-Stage | Dosemetic | non consultancy | template 1