## SRM_SCREEN_DESIGN_PLAN_2021
SRM-Development Plan for Supplier and Department user Functionality
S.No | Functionality Name | Sub-Functionality | Screen Name | Person Allocated | Technology | Planning Start Date | Planning End Date | Actual Start Date | Actual End Date | Status
1 | User Selection |  | User Selection Page for Login or Register for supplier and Department user | Sanjay and Augustin | Laravel | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-07-06 | completed
2 | Login Page |  | Login Page for Supplier and Department user | Sanjay and augustin | Laravel | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-07-06 | completed
4 | verfication page |  | Department user verification | Augustin | laravel | 2021-07-06 | 2021-07-06 |  |  | pending
5 | creation of master screens |  | Nature of work master and materials master | Augustin | laravel | 2021-07-07 | 2021-07-07 | 2021-07-07 | 2021-07-07 | Completed
SUPPLIER REGISTRATION AND DETAILS ENTRY PROCESS
6 |  | General Details | Creation of general profile with attachements(alfesco) | Sanjay | Laravel | 2021-07-08 | 2021-07-09 | 2021-07-08 | 2021-07-09 | completed
7 |  |  | Creation of Sole Porprietorship with attachements(alfesco) | Sanjay | Laravel | 2021-07-09 | 2021-07-10 |  |  | Workin progress
8 |  |  | creation of partnership with attachements(alfesco) | Sanjay | Laravel | 2021-07-10 | 2021-07-11 |  |  | Workin progress
9 |  |  | creation of Corporate concern | Sanjay | Laravel | 2021-07-11 | 2021-07-12 | 2021-07-07 | 2021-07-07 | completed
10 |  |  | creation of Director and principal officer with attachements (alfesco) | Sanjay | Laravel | 2021-07-12 | 2021-07-13 |  |  | Workin progress
11 |  |  | Creation Page For Partnership Concern(Adding the Profile details of the partners) | Sanjay | Laravel | 2021-07-13 | 2021-07-13 | 2021-07-07 | 2021-07-07 | completed
12 |  |  | Edit of genral profile with attachements | Sanjay | Laravel | 2021-07-14 | 2021-07-15 |  |  | Workin progress
13 |  |  | Edit sole porpritorship | Sanjay | Laravel | 2021-07-15 | 2021-07-15 |  |  | Workin progress
14 |  |  | Edit For Partnership Concern(Editiong the Profile details of the partners) with attachements | Sanjay | Laravel | 2021-07-16 | 2021-07-16 | 2021-07-08 | 2021-07-08 | Completed
15 |  |  | (Editing the Profile details of the Directors and principa officers with attachements | Sanjay | Laravel | 2021-07-16 | 2021-07-16 | 2021-07-08 | 2021-07-08 | Completed
|  |  | Show page and soft delete of general profile | Sanjay | Laravel | 2021-07-16 | 2021-07-16 |  |  | progress
16 |  |  | perivious notes section for general profile inserting queries for Audittrail and notfications | Sanjay | Laravel | 2021-07-19 | 2021-07-19 |  |  | Work in progress
14 |  |  | unit testing | Sanjay | Laravel | 2021-07-19 | 2021-07-19 | 2021-07-08 | 2021-07-08 | Completed
16 |  | Technical Details | 3 stages of add Technical Details of the Supplier | Augustin | Laravel | 2021-07-08 | 2021-07-08 | 2021-07-08 | 2021-07-08 | Completed
17 |  |  | Edit Page for Technical Details | Augustin | Laravel | 2021-07-09 | 2021-07-09 | 2021-07-09 | 2021-07-08 | Completed
18 |  |  | perivious notes section for technical profile inserting queries for Audittrail and notfications | Augustin | laravel | 2021-07-09 | 2021-07-09 | 2021-07-08 |  | Work in progress
19 |  |  | View page for techincal details | Augustin | laravel | 2021-07-09 | 2021-07-09 | 2021-07-08 | 2021-07-08 | completed
20 |  |  | unit testing | Augustin | Laravel | 2021-07-09 | 2021-07-09 | 2021-07-08 | 2021-07-08 | Completed
21 |  | Experience | creation of Experience Details | Augustin | Laravel | 2021-07-09 | 2021-07-09 | 2021-07-09 | 2021-07-10 | Completd
22 |  |  | Multiple Attachments and show page for Experience | Augustin | Laravel | 2021-07-12 | 2021-07-12 | 2021-07-12 | 2021-07-12 | Completed
23 |  |  | Edit Page for Experience Details with update the attcahemets | Augustin | laravel | 2021-07-12 | 2021-07-12 | 2021-07-12 | 2021-07-12 | Completed
24 |  |  | perivous notes in edi page and audit trail and notifications and unit testing | Augustin | Laravel | 2021-07-12 | 2021-07-12 | 2022-07-12 | 2022-07-12 | Work in progress
25 |  | Financial | Add Oprations of Financial Details | Augustin | Laravel | 2021-07-13 | 2021-07-13 | 2021-07-13 | 2021-07-13 | Completed
26 |  |  | Multiple Attachments and show page for Financial | Augustin | Laravel | 2021-07-14 | 2021-07-14 | 2021-07-14 | 2021-07-14 | completd
|  |  |  | augustin | Laravel | 2021-07-15 | 2021-07-15 | 2021-07-15 | 2021-07-15 | pending
27 |  |  | Edit Page for Financial Details | Augustin | Laravel | 2021-07-14 | 2021-07-01 | 2021-07-14 | 2021-07-14 | Completed
|  |  | unit testing technical , experience and finiacial profile | Augustin | laravel | 2021-07-15 | 2021-07-15 | 2021-07-15 | 2021-07-15 | Work in progress
28 | Supplier Approval-Supplier Details View Page(Reuse of the view screen of the suppplier Details in Department user screen ) | General Details-Tab1 | General Details of the Supplier with attachments | Sanjay | Laravel |  |  |  |  | pending
30 |  |  | Listing of the Partners if the constitution is Partnership | sanjay | Laravel |  | 2021-07-16 | 2021-07-16 | 2021-07-16 | pending
31 |  |  | Details of the Partners | sanjay | Laravel | 2021-07-17 | 2021-07-17 | 2021-07-17 | 2021-07-17 | pending
32 |  |  | Listing of the Directores and principal officers-if the constitution is corporate | Sanjay | Laravel | 2021-07-19 | 2021-07-19 | 2021-07-19 | 2021-07-19 | pending
33 |  |  | Sole properitorship Details Page | Snajay | Laravel |  | 2021-07-16 |  |  | pending
34 |  | Technical Details Tab2 | Technincal Details of the Supplier with attachments | Augustin | Laravel | 2021-07-16 | 2021-07-16 | 2021-07-16 | 2021-07-16 | pending
35 |  | Experience Details Tab4 | Experience Details of the Supplier with attachments | Augustin | Laravel | 2021-07-16 | 2021-07-17 | 2021-07-16 | 2021-07-17 | pending
36 |  | Financial Details Tab3 | Financial Details of the Supplier with attachments | Augustin | Laravel | 2021-07-19 | 2021-07-20 | 2021-07-19 | 2021-07-20 | pending
37 | intergrating of notifications and auditral | Department user and Supplier |  | Augustin and sanjay | laravel | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-07-20 | pending
38 | Unit testing the whole flow | Department user and Supplier |  | Augustin and sanjay | laravel | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | pending
39 | Hosting and SIT testing |  |  | Augustin and sanjay |  | 2021-07-22 | 2021-07-22 | 2021-07-22 | 2021-07-22 | pending
40 | demo |  |  | Augustin and sanjay |  | 2021-07-23 | 2021-07-23 | 2021-07-23
40 | UAM

## Sheet1
Audit Trail
System Alert and Email notifications (Draft)
FAQ
Supplier User Profile
Wordpress- Landing Page
Database Design
Screen Design Completion, Review and Signoff